## Sheet1
# | Metric Name | Requirement | Description | Shannon Comments | Priority | Status | Date Completed | Notes/Status | SME/Data Owner
1 | Predictibility Models for Risk and Visit Indicators | Readmit Risk Indicator and Preventable ER visit. Must prioritize recently discharged members with high readmit risk. Must rank members by likelihood score and highlight top tiers. Must include predictive risk scoring and stratification; highlight top risk tiers (top 1%, 2–5%). Must support industry-aligned or explainable risk methodology (e.g., standard/vendor-backed models where possible). | Identifies members based on risk stratification (high/mod/low, or yes/no flag) including likelihood of readmit or ER utilization. Identifies members recently admitted/discharged with likelihood of 30-day readmission. Identifies members at risk for avoidable ER or preventable visits. |  | High | Pending Source |  | https://centene.sharepoint.com/teams/CenteneDataAnalytics/SitePages/AI-Center-of-Excellence-Portfolio.aspx?web=1&xsdata=MDV8MDJ8fDc1ZjliZDQwN2Q4ZjQ2ODlkYjgyMDhkZWQyMmYxYzBlfGY0NWNjYzA3ZTU3ZTRkMTViZjZmZjZjYmNjZDJkMzk1fDB8MHw2MzkxNzkyOTY5MDkyMjA3Mzh8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKRFFTSTZJbFJsWVcxelgwRlVVRk5sY25acFkyVmZVMUJQVEU5R0lpd2lWaUk2SWpBdU1DNHdNREF3SWl3aVVDSTZJbGRwYmpNeUlpd2lRVTRpT2lKUGRHaGxjaUlzSWxkVUlqb3hNWDA9fDF8TDJOb1lYUnpMekU1T20xbFpYUnBibWRmVG5wVk0wOUhXbTFOYlZGMFRVZFNiVnBUTURCUFZGRXdURmRLYTA5RVRYUk9Na1p0V1ZSQ2ExcHRWVEpPVkVwb1FIUm9jbVZoWkM1Mk1pOXRaWE56WVdkbGN5OHhOemd5TXpNeU9EZzVORGc1fGFkYTVhYTllMjkzNzQxMDM3OGY1MDhkZWQyMmYxYzBlfDk1ZTliMDA5MjlkNTRkNGY5N2Y2OTRiOGRhMWM3NGM5&sdata=eGFxeCtjbHdHRk8zN2VqdFI3djJ6VTdkY3lrUUh3bUsyRVhRR0RKT3Yvdz0%3D&ovuser=f45ccc07-e57e-4d15-bf6f-f6cbccd2d395%2CCN476879%40centene.com
2 | Identification of High-Cost Members | Must enable isolation of highest-cost members for outreach prioritization. | Identifies members with highest cost/utilization to support targeting. | Put in member list | Medium-low | Complete |  | Already included in PPA.
3 | Linkage of High Risk Members to Care Management Engagement Status | Must clearly distinguish engaged vs not engaged vs unable to reach for provider action. | Shows whether high-risk members are engaged, not engaged, or unreachable. | Trend on CM Partnership page | High | Follow Up |  | Need to clarify the definition of "engaged" and "high risk" for care management
4 | Geographical Data Sorting | Groups sorted against like-providers | Allows for provider groups comparison. | I believe this can be a filter, but need criteria | High | Complete |  | Functionality is available, requirements to compare are still needed. What would the list of comparisons look like (ID metrics)?
5 | Provider-Level Attribution & Population Views | Must allow members to be grouped and analyzed by provider (TIN, group, PCP). Must support population-level views by provider for engagement and CM action. | Enables analysis of member populations by assigned/provider of care to support provider engagement workflows. | Pages + Filters (Cannot get PCP level???) | High | Complete |  | Groupings exist to the TIN level. Already in PPA
6 | Last Interaction Date | Must be prominent; used to determine freshness of engagement. | Most recent direct interaction date with care manager. | Added to member list | High | Pending Source |  | Member level - dependent on data source
7 | Last Interaction Status | Must support outreach prioritization and gap identification. | Outcome of most recent outreach (successful, attempted, no response). | Added to member list | High | Pending Source |  | Member level - dependent on data source
8 | Care Manager Assigned to Member | Must support visibility into ownership of member care. | Indicates whether a member has an assigned care manager. | Added to member list | Low | Pending Source |  | Member level - dependent on data source
9 | Care Manager Name and Contact Information | Must enable provider-care team communication. | Provides care manager details for coordination. | Added to member list | Medium | Pending Source |  | Member level - dependent on data source
10 | Care Management Eligibility | Must define eligible population and actively enrolled population, but not primary focus for providers. | Identifies members eligible for care management programs. | On CM Partnership page | Low | Pending Source |  | Member level - dependent on data source
11 | Care Management Count | Aggregated metric; less relevant for provider action. | Total members actively in care management programs. | On CM Partnership page | Low | Pending Source |  | Member level - dependent on data source
12 | Care Management Enrollment Rate | Track % of eligible members actively enrolled in care management. |  | On CM Partnership page | Medium | Pending Source |  | Member level - dependent on data source
13 | Counts of Care Management by Type/Category | Useful for operational insight, not provider decision-making. | Distribution of CM cases by type/category. | On CM Partnership page | Low | Pending Source |  | Member level - dependent on data source
14 | Utilization KPIs (Core Metrics) | Standardized KPIs: ER visits per 1000, admissions per 1000, readmission rate (%). Ability to drilldown from actionable population (who the members are - high utilizers) | Provides baseline utilization performance metrics for tracking and comparison. | on Panel Overview and Trend pages + Filters (need high cost, too?) | Medium | Follow Up |  | Ability to have per 1000 + high cost included. Already in PPA
15 | Risk Stratification KPIs (Top Dashboard Metrics) | Must prominently display overall risk distribution (high/mod/low) at dashboard level. | Summary KPI showing population risk segmentation. | on Panel Overview | High | Follow Up |  | Already in other views of PPA (high risk, distro, etc.) Further clarification needed